## Munkalap1
Task ID | Name | Description | Workforce | Estimated Difficulty | Actual Difficulty | Date Of Finish
0 | Descriptions | Short Description of the Task | People undertaking the task | In units (1 unit ≈ 30 mins) | How long it actually took | Date on which task was finished
1 | Stakeholders | Identification, classification and description of stakeholders | Andrew | 2022-01-02 | 3 | 2022-02-18
2 | Personas | Create Personas based on the stakeholders (≈5) | Patrik,Madhav | 2022-03-04 | 4 | 2022-02-18
3 | User Stories | Write user Stories based on the stakeholders (≈25) | David, G | 2022-05-06 | David+3 | 2022-02-21
4 | Report | Put together report | Adam | 2022-03-04
5 | Risk Analysis | Figure out risks, and mitigation strategies | Andrew | 2022-01-02
6 | Product Backlog | Write the Product Backlog | Patrik | 2022-01-02 | 6 | 2022-02-21
7 | Sprint Planning | Sprint and Envisioning backlog made as well as burndown chart | Patrik,Madhav | 2 | 3 | 2022-02-21
MoSCoW Prioritisation: |  | Must | Should | Could | Won't