## Munkalap1
Task ID | Name | Description | Workforce | Estimated Difficulty | Actual Difficulty | Date Of Finish
0 | Descriptions | Short Description of the Task | People undertaking the task | In units (1 unit ≈ 30 mins) | How long it actually took | Date on which task was finished
1 | Individual display | Side-on and Top-Down visualisations can be displayed individually |  | 6
2 | Centerline | Runway centerline displayed on top-down view |  | 4
3 | TORA | Runway strip displayed in both views and TORA indicated |  | 6
4 | Clearway and TODA | Clearway and new TODA displayed on both views |  | 4
5 | Stopway and ASDA | Stopway and new ASDA displayed on both views |  | 4
6 | LDA | LDA calculated and displayed on both views |  | 4
7 | Displaced threshold | Displaced threshold calculated and displayed on both views |  | 6
8 | Obstacle display | Obstacles displayed on both views |  | 6
9 | Calculations | Code calculates new runway length given 1 obstacle and parameters |  | 6
10 | Calculation Display | Calculation results displayed side-by side with original values |  | 6
11 | Sprint Planning | Create sprint backlog for next increment and burndown chart for this one |  | 3
12 | Report | Write the report for the current increment |  | 4
MoSCoW Prioritisation: |  | Must | Should | Could | Won't