## Munkalap1
Task ID | Name | Description | User Story | Increment | Estimated Difficulty | Actual Difficulty
0 | Name of task | Short Description of the Task | Which user story mentions is | When it will be done | In units (1 unit ≈ 30 mins) | How long it actually took
1 | Individual display | Side-on and Top-Down visualisations can be displayed individually | 9 | 1 | 6
2 | Simultaneous display | Side-on and Top-Down visualisations can be displayed simultaneously | 13 | 2 | 6
3 | Centerline | Runway centerline displayed on top-down view | 12 | 1 | 4
4 | TORA | Runway strip displayed in both views and TORA indicated | 32 | 1 | 6
5 | Clearway and TODA | Clearway and new TODA displayed on both views | 20 | 1 | 4
6 | Stopway and ASDA | Stopway and new ASDA displayed on both views | 22 | 1 | 4
7 | Threshold | Thershold indicators and designators displayed on both views | 33 | 2 | 4
8 | LDA | LDA calculated and displayed on both views | 14 | 1 | 4
9 | Takeoff/Landing Direction | Takeoff and landing directions are displayed on both views | 24 | 2 | 4
10 | RESA | RESA calculated and displayed on both views | 23 | 2 | 4
11 | Angles | Offsets caused to ALS and TOCS calculated and displayed on side-view | 21 | 2 | 4
12 | Displaced threshold | Displaced threshold calculated and displayed on both views | 16 | 1 | 6
13 | Obstacle display | Obstacles displayed on both views | 17 | 1 | 6
14 | Cleared and Graded | Cleared and graded areas displayed on top-down view | 19 | 2 | 4
15 | Calculations | Code calculates new runway length given 1 obstacle and parameters | 18 | 1 | 6
16 | Obstacles | Pre-defined obstacles implemented and usable | 11 | 3 | 8
17 | Calculation Display | Calculation results displayed side-by side with original values | 5 | 1 | 6
18 | Show Your Work | Calculation steps displayed on request | 3 | 2 | 6
19 | XML | Import and export details of obstacles and airports as well as results from files (XML) | 1 | 3 | 8
20 | Runway Rotation | Automatically rotate runway so it matches compass direction | 6 | 2 | 8
21 | Update Runway | Views update in real time if new runway, obstacle, data selected or changed | 2 | 2 | 10
22 | Notifications | Notifications must be given to user whenever data changes | 10 | 2 | 6
23 | Maps | Overlay real world images on display | 25 | 3 | 8
24 | Zoom | The ability to zoom and pan views | 26 | 3 | 8
25 | 3D | 3D Visualisation | 27 | 3 | 10
26 | Export | Export display in JPEG, PNG, etc. | 28 | 3 | 8
27 | Assistive technologies | API support for assistive technologies | 29 | 3 | 10
28 | Colour Schemes | Alternative colour schemes present | 30 | 3 | 2
29 | Printing | Ability to print out results | 31 | 3 | 6
MoSCoW Prioritisation: |  | Must | Should | Could | Won't